## Sheet1
LONG-TERM CONTRACTS - US GAAP / IFRS
Assume that XYZ Construction Corp. has a contract to build an office building for $5,000,000 and a reliable estimate of the contract's total cost is $4,000,000. Project cost incurred by XYZ is as follows:
Contract Revenue: | 5000000
Year |  | 2015 | 2016 | 2017 | Total
Cost incurred |  | 2000000 | 800000 | 1200000 | 4000000
If outcome can be relliably measured, determined profit and revenue under US GAAP and IFRS
Year |  | 2015 | 2016 | 2017 | Total
% Completion |  | 50% | 20% | 30% | 100%
Revenue |  | 2500000 | 1000000 | 1500000 | 5000000
Cost |  | -2000000 | -800000 | -1200000 | -4000000
Profit |  | 500000 | 200000 | 300000 | 1000000
If outcome can't be relliably measured, determined profit and revenue under US GAAP and IFRS
UNDER IFRS
Year |  | 2015 | 2016 | 2017 | Total
Revenue |  | 2000000 | 800000 | 2200000 | 5000000
Cost |  | -2000000 | -800000 | -1200000 | -4000000
Profit |  | 0 | 0 | 1000000 | 1000000
UNDER GAAP
Year |  | 2015 | 2016 | 2017 | Total
Revenue |  | 0 | 0 | 5000000 | 5000000
Cost |  | 0 | 0 | -4000000 | -4000000
Profit |  | 0 | 0 | 1000000 | 1000000